## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
Add | Store Library of Songs | 3
| Implement Library Page (display songs list, display song details, can open add) | 7
| Add Song (enter song info, save song, cancel) | 3
| Integrate error handling/messaging for missing required information | 3
| Integrate valididation for information entered/missing | 2
Rank | Edit lib page to display rank | 2
| Edit add page to add rank | 2
| Edit Library of songs to store rank | 2
Tags | Edit library of songs to store tags | 2
| Edit library page to display tags | 2
| Edit add page to add tags (can't add duplicate tags, autocomplete tags) | 3
| Integrate error handling/messaging for missing required information | 3
| Integrate valididation for information entered/missing | 2
Edit | Update song in the system, whether it is complete or not | 2
| Edit song via edit option button in UI | 2
| Confirmation dialog for information entered is presented | 2
| Integrate validation for information entered/missing | 3
| Integrate error handling/messaging for missing required information | 3
Generate Playlist | Provide seed information with target playlist length and some ranked songs | 2
| Generates playlist with no repeated songs | 5
| If no length, generate 10-15 songs | 3
| If no rank or seed, generate playlist based on available information | 2
| If no info provided, generate 10-15 songs based on available information | 2
Select | Ability to select a song and have it's information presented upon selection | 3
*Refer to Documentation for context*
| Estimate Totals | 65 | 0 | 0 | 0 | 0
Requirements.pdf
Product Backlog.xlsx
PlayList Generator - Use Case Scenarios.pdf
high-quality-professionally-developed-ui-design.jpg